## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-05-2B-Animal Auxiliaries
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | MO; 10/25/2023;
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | MO; 10/25/2023;
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | MO; 10/25/2023;
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | MO; 10/25/2023;
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | MO; 10/25/2023;
As a user I want to view all of the needs so that I can see what the organization needs. | Given I submit a request to the webpage when I view an organizations cupboard then I view all needs for a given organization | Pass | MO; 10/25/2023;
As a helper I want a shopping basket that holds needs so that I can store the things I will fund. | Given a user is a helper when they view needs then I expect them to have a basket to store things. | Pass | CB; 10/25/2023;
| Given that I am a helper on the cupboard page, then I must see a means to naviagte to my basker | Pass | CB; 10/24/2023;
| Given that I am not in my basket, when I choose my basket then I am taken to my basket. | Pass | CB; 10/24/2023;
| Given that I am in my basket I expect to be able to view the needs that I have previously added to the basket | Pass | CB; 10/24/2023;
| Given that I am in my basket I expect to be able to remove needs from my basket | Pass | CB; 10/25/2023;
As a Helper I want to save Needs to my Basket so that I can later fund them | Given that I am a helper on the needs page, when I view a need then I expect to be able to add that need to my basket from the needs page. | Pass | CB; 10/25/2023;
| Given that I have added a need to my basket I expect it to remain in my basket until I remove it | Pass | CB; 10/25/2023;
As a Helper I want to remove a need from my basket so someone else can fund it | Given that I am a helper viewing my basket then I expect to see a means of removing needs from my basket | Pass | CB; 10/25/2023;
| Given that I have requested to remove a need from my basket I expect it to no longer appear listed in my basket | Pass | CB; 10/24/2023;
| Given that I have removed a need from my basket I expect it to remain removed from my basket after I leave and return to the site. | Pass | CB; 10/24/2023;
As a user I want to be able to login to the site so that I can save and view my previous actions | Given a user opens the site, they expect to view a prompt to enter login credentials. | Pass | MO; 10/21/2023;
| Given a user enters Manager login credentials, they expect to be taken to the u-fund manager home page. | Pass | MO; 10/24/2023;
| Given a user enters Helper login credentials, they expect to be taken to the u-fund helper home page. | Pass | MO; 10/24/2023;
| Given a user has been authenticated and taken to their respective homepage, they expect their associated data to be saved from their last interaction with the site. | Pass | MO; 10/24/2023;
As a manager I want to be able to manage the contents of my organizations cupboard. | Given a Manager is viewing their u-fund home screen, they should see a means of navigating to their cupboard. | Pass | TC; 10/24/2023;
| Given a Manager chooses their cupboard, they expect to be taken to their cupboard. | Pass | TC; 10/24/2023;
| Given a Manager is viewing their cupboard, they should see a means of searching through their needs. | Fail | TC; 10/25/2023; Searching not provided on front end for manager
| Given a Manager is viewing their cupboard, they should see a means of selecting a need. | Pass | TC; 10/25/2023;
| Given a Manager has selected a need, they should see a means of editing the selected need. | Pass | TC; 10/25/2023;
| Given a Manager has edited a selected need, they expect the edited version of the need to appear in their cupboard. | Pass | TC; 10/25/2023;
| Given a Manager has edited a need, they expect that need to be removed from any Helper baskets that it was previously in. | Fail | TC; 10/25/2023; Means of removing a need from helper baskets post update not implemented
| Given a Manager has selected a need, they should see a means of deleting the selected need. | Pass | TC
| Given a Manager has requested to delete a need, they expect to be prompted with a confirmation that they want to permanently delete the need. | Fail | TC; 10/25/2023; Confirmation not given/required
| Given a Manager confirms they want to delete a need, they expect that need to no longer be shown in their cupboard. | Pass | TC; 10/25/2023;
| Given a Manager confirms they want to delete a need, they expect that need to no longer be shown in any Helper baskets it was previously in. | Pass | TC; 10/25/2023;
| Given a Manager has selected a need, they expect to see a means of retiring the need. | Pass | TC; 10/25/2023;
| Given a Manager has requested to retire a need, they expect to still see the need listed in their cupboard with some indication that it has been retired. | Pass | TC; 10/25/2023;
| Given a Manager has selected a need that is retired, they expect to see a means of unretiring that need. | Pass | TC; 10/25/2023;
| Given a Manager has requested to unretire a need they expect to be able to view it in their cupboard with no indication that it is retired. | Pass | TC; 10/25/2023;
| Given a Manager has requested to unretire a need, they expect it to be visible in their cupboard to Helpers. | Pass | TC; 10/25/2023;
| Given a Manager is viewing their cupboard, they expect to see a means of creating a new need. | Pass | TC; 10/25/2023;
| Given a Manager has requested to create a new need, they expect to view a prompt where they can describe their new need. | Pass | TC; 10/25/2023;
| Given a Manager is viewing the request to create a need they expect to see a means of submitting the new need. | Pass | TC; 10/25/2023;
| Given a Manager submits a complete request to create a new need, they expect the new need to be shown in their cupboard. | Pass | TC; 10/25/2023;
| Given a Manager submits an incomplete request to create a new need, they expect to see a message saying their need could not be created. | Pass | TC; 10/25/2023;
As a Helper I want to fund needs so that I can help that organization | Given a user is logged in as a helper, they should see a means of viewing the cupboard. | Pass | SP; 10/25/2023;
| Given a user is logged in as a helper, they should see a means of viewing the cupboard. | Pass | SP; 10/25/2023;
| Given a helper is attempting to search the cupboard, they should see a means of searching by name, type, or price. | Pass | SP; 10/25/2023;
| Given a helper has submitted a search request, they expect to see a list of Needs from the cupboard that match their search. | Pass | SP; 10/25/2023;